Timeline with Milestones and Fallback Plan for Project 2

March 7, 2003

Team 4 – Justin Fuller, Rahul Kotamaraju, Matthew Lawrence

1.0 Overview

The schedule for Project 2 will run from Wednesday, March 5, 2003, to Monday, March 31, 2003.  Milestones for the project will consist of due dates assigned by Dr. Dean Hougen as well as goals set by the team.  Milestones set by the team will coincide with the various phases of the project.  Each team member will be responsible for ensuring that he heeds and meets each milestone as appropriate.  Additionally, all team members will hold each other accountable.  In the event that any of the milestones is missed, the fallback plan will be strictly adhered to.  In this way, the team will remain on-schedule with sufficient time for each task, resulting in an optimal overall solution.

2.0 Milestones

The schedule for the second project will consist of seven major milestones – planning, design, construction, code, test, demonstration, and documentation.  For this project, the team will apply a “measure twice, cut once” philosophy.  With this approach, the team will spend a great deal of time in the design phase so that less time will be required during the remaining phases, particularly the test phase.  Milestones for the remaining phases will be assigned such that the team will be able to meet all deadlines imposed by Hougen.  Additionally, the team will work around the week of Spring Break (March 15 - 23) since the team will be unable to convene during that period.  However, this week may be used as a fallback if necessary.

2.1 Planning (March 7)

The planning milestone for the project will see the establishment of the team’s organization and timeline.  The team will delineate the various phases of the project and will decide which members will be responsible for each task.  Additionally, the team will assign milestones to the project and will create a fallback plan.  Because Hougen has set a due date of March 7 for the organizational and timeline reports, the milestone for planning will be one day prior – March 6.  This milestone has already been met, so no fallback plan will be necessary.

2.2 Design (March 14)

The design milestone will be met only when the team has established a single, robust architecture for the robot construction and control.  The design phase is the crux of the project’s lifecycle.  Here the team will seek to develop a specific design that will be capable of performing all of the required tasks.  If this phase is executed properly, no major design changes will be required after the design milestone.  This will allow the team to devote the test phase to testing the robot, rather than re-designing it.  In order to allow for such a thorough design, the milestone will be set at March 14.  It is highly imperative that the team meet this milestone.  However, if the team is unable to establish a satisfactory design, Rahul Kotamaraju will create a generic design for the robot, and Justin Fuller will design the sensor array and develop the corresponding code.  The two will seek to work in such a fashion that their designs will be readily compatible upon return from Spring Break (March 22).

2.3 Construction (March 22)

The construction milestone will be complete following the full assembly of the robot as determined in the team’s design.  Because Rahul Kotamaraju is solely responsible for the construction phase, it can be completed autonomously during the week of Spring Break.  Subsequently, assembly must be completed by the time team reconvenes on March 22.  If this milestone is not met, Justin Fuller will assume responsibility for its completion due to his previous experience in assembly.

2.4 Code (March 22)

The code milestone requires the implementation of the robot’s artificial intelligence in Interactive C.  As with construction, this phase will be completed by a single member, apart from the rest of the team.  Once again, the code must be finalized and ready for testing by March 22, the end of Spring Break.  If the milestone elapses, coding responsibilities will be assumed by Matthew Lawrence, the team’s IC expert.

2.5 Test (March 26)

The test milestone will mark the confirmation of the robot’s compliance with all required specifications.  Here, the team will test every conceivable aspect of the robot’s operation to ensure correctness.  If the design phase is properly completed, the team will meet with no failures and will need only to tweak the robot’s parameters.  Hougen has set the demonstration dates at March 27 - 28, so the team must complete testing by March 26.  If the team cannot meet this deadline, the members will begin sleeping in shifts and working around-the-clock to correct all problems.

2.6 Demonstration (March 28)

The demonstration milestone indicates the exhibition of the team’s robot before Hougen.  Here, the team will present the robot, and Hougen will observe as it performs all of the required tasks.  Hougen has set the dates for demonstration at March 27 – 28, so the milestone must be completed by March 28.  Because of the nature of this deadline, a fallback plan will be feasible only in the case of extreme circumstances, such as illness by all team members, and will have to be negotiated uniquely with Hougen.

2.7 Documentation & Presentation (March 29)

The documentation and presentation milestone indicates the completion of the team’s final report and presentation.  For this goal, the team must prepare a detailed report explaining the robot’s construction and operation.  The team will also compose and present a brief, high-level speech concerning the robot.  This milestone will be completed as quickly as possible following conclusion of the testing phase; the target date will be March 29.  If this deadline cannot be met, the responsibilities will be handed off to Rahul Kotamaraju, who has prior experience with reports and presentations.